# Project Plan V2 — Task Assignments

Project Manager: Blessing   |   Team: Divine, Sam, Obi, Nhlakanipho

Note: Data Modeling, ETL migration, Google Auth setup, and Google OAuth Consent Screen tasks are excluded from team assignments.

| # | Task | Due Date | Assignee(s) | Difficulty |
| --- | --- | --- | --- | --- |
| 1 | Update Pydantic to use UUIDs / integers for primary keys and flatten into separate relational models | 18–20 May | Sam | Medium |
| 2 | Update Service Layer — refactor to use Supabase SDK (remove MongoDB middleware) | 18–19 May | Divine | High |
| 3 | Replace async client dependencies connecting to Mongo with Supabase connections | 18–24 May | Divine & Obi | High |
| 4 | Add Supabase to dependencies | 18–24 May | Nhlakanipho | Low |
| 5 | Handling of Nested Data — rewrite functions using Supabase syntax across relational tables | 18–24 May | Obi & Sam | High |
| 6 | Replace backend permission logic with Row Level Security (RLS) Policies in Supabase | 18 May – 2 June | Divine & Nhlakanipho | High |
| 7 | Update error handling / error-catching logic for SQL-specific cases | 18 May – 2 June | Sam | Medium |
| 8 | Rewrite CRUD logic (Query refactor) — update to use Supabase table/row logic and SQL syntax | 18 May – 2 June | Obi & Divine | High |
| 9 | Screen integration — each screen connected to new data source | 18 May – 2 June | Nhlakanipho & Sam | High |
| 10 | Install Chart.js & Design new cells report | 5 June | Nhlakanipho | Medium |
| 11 | Design approval & Implement Stats Graph dev work as per design | 6–12 June | Obi & Sam | High |
| 12 | Local testing | 15–16 June | All team | Medium |
| 13 | Peer reviews | 16–17 June | Divine & Nhlakanipho | Low |
| 14 | Code review | 17 June | Blessing (PM) | Low |
| 15 | QA Testing | 18 June | Sam & Obi | Medium |
| 16 | Merging of pull requests | 19 June | Divine | Low |
| 17 | Post merge checks and testing | 19 June | Nhlakanipho | Low |
| 18 | Go Live | 22 June | Blessing (PM) | Low |
| 19 | Post Live Checks and Rollback plan for any system-breaking issues | 22–24 June | Blessing & All team | High |

Difficulty Legend

| High | Complex — assigned to 2 people |
| --- | --- |
| Medium | Moderate complexity — single owner |
| Low | Straightforward — single owner |

Team Summary

| Member | Key Responsibilities |
| --- | --- |
| Divine | Service Layer refactor, Async client replacement, RLS Policies, CRUD refactor, PR merging |
| Sam | Pydantic update, Nested Data, Error handling, Stats Graph, QA Testing |
| Obi | Async client replacement, Nested Data, CRUD refactor, Stats Graph, QA Testing |
| Nhlakanipho | Supabase dependency, RLS Policies, Screen integration, Chart.js, Peer review, Post merge checks |
| Blessing (PM) | Code review oversight, Go Live coordination, Post Live checks & rollback planning |